## Business Plan
Артикль | Описание | Конкурент | Цена | Средняя цена | Мин.цена | Макс.цена | Ссылка
1 | Marketing Research Tactical Plan | J. Dow | 70 | #REF! | #REF! | #REF! | #REF!
1.1 | Scope Definition Phase | J. Dow | 10 | #REF! | #REF! | #REF! | #REF!
1.1.1 | Define research objectives | J. Dow | 3 | #REF! | #REF! | #REF! | #REF!
1.1.2 | Define research requirements | S. Jones | 7 | #REF! | #REF! | #REF! | #REF!
1.1.3 | Determine in-house resource or hire vendor | J. Dow | 2 | #REF! |  | #REF! | #REF!
1.2 | Vendor Selection Phase | J. Dow | 19 | #REF! | #REF! | #REF! | #REF!
1.2.1 | Define vendor selection criteria | J. Dow | 3 | #REF! | #REF! | #REF! | #REF!
1.2.2 | Develop vendor selection questionnaire | S. Jones, T. Wates | 2 | #REF! | #REF! | #REF! | #REF!
1.2.3 | Develop Statement of Work | S. Jones | 4 | #REF! | #REF! | #REF! | #REF!
1.2.4 | Evaluate proposal | J. Dow, S. Jones | 4 | #REF! | #REF! | #REF! | #REF!
1.2.5 | Select vendor | J. Dow | 1 | #REF! | #REF! | #REF! | #REF!
1.3 | Research Phase | G. Lee | 47 | #REF! | #REF! | #REF! | #REF!
1.3.1 | Develop market research information needs questionnaire | G. Lee | 2 | #REF! | #REF! | #REF! | #REF!
1.3.2 | Interview marketing group for market research needs | G. Lee | 2 | #REF! | #REF! | #REF! | #REF!
1.3.3 | Document information needs | G. Lee, S. Jones | 1 | #REF! | #REF! | #REF! | #REF!